## Tasks
Tasks
Completed?
Pre-planning and preparation
| Get PurplePen running | y
| OCAD map | y
| Decide on courses / lengths | y
Planning the courses
| Start/Finish location | y
| Plan courses | y
Mark control sites
Produce event maps and control descriptions
Before the event
Equipment prep
On the day
| Putting out controls |  | Complete at least an hour before first start time
Bringing in controls
After the event
Returning equipment

## Courses
Definition
GLOSS is a series of races run by the clubs in and around London. There are two courses: the GLOSS course which is about 3½ to 4½ km (with optional extension to around6 km) and is of moderate navigational difficulty and a ‘Yellow’ course which is about 2km with easier navigation.
Lengths:
GLOSS: 4km - this equates to Light Green
Extension: 2km
Yellow: 2km
Yellow
Navigate along obvious line features. Leave a line feature to go to a visible control site near it then return to that line feature
i.e. controls don't have to be on the line feature but need to be visible from it
Line features don't have to be paths
Need to think about attack points
Green
Use contour features
This must mean re-entrants, spurs, etc.
Need to think about attack points
Route choice
Catching features
General
The control feature should be visible within 10m or 10% of the distance from the nearest attack point

## Notes
Previous event
| GLOSS | 16 controls
| GLOSS Ext | 25 controls (1 is the GLOSS finish)
| Yellow | 13 controls | only 2 shared with GLOSS
Up the hill might be too tough for the yellow - keep it aournd the field at the bottom

## Costs
Date | Description | Cost
2024-02-18 | BOF Planner training | 10
2024-03-02 | Trip to Reigate from home (2x10mi)